## Sheet1
Project Name |  | Cinema Café
Start Date |  | 22nd May
End Date |  | 26th May
Overall Progress |  | 40%
Developers Team
Task Name | Sub Features | Responsible | Start | End | Days | Status
Sprint 1 |  | Aleena and Team | 22nd May | 26th May | 5 | In progress
Documentation |  | Aleena,Venu,Soumya,Ravi,SwamiPrasadam | 22nd May | 22nd May | 1 | Completed
Login Module | Register,Login | Aleena,Venu,Soumya,Ravi,SwamiPrasadam | 23nd May | 23nd May | 1 | Not Started
Login Module | Forgot Password,Edit Profile | Aleena,Venu,Soumya,Ravi,SwamiPrasadam | 24rd May | 24rd May | 1 | Not Started
Admin Module | Adding Movies,Adding/updating price | Aleena,Venu,Soumya,Ravi,SwamiPrasadam | 25th May | 26th May | 2 | Not Started
Testers Team
Task Name | Sub Features | Responsible | Start | End | Days | Status
Sprint 1 |  | Deepak and Team | 22nd May | 26th May | 5 | In progress
Documentation |  | Deepak, Indu, Sneha | 22nd May | 22nd May | 1 | Completed
Login Module | Register,Login | Deepak, Indu, Sneha | 23nd May | 23nd May | 1 | Not Started
Login Module | Forgot Password,Edit Profile | Deepak, Indu, Sneha | 24rd May | 24rd May | 1 | Not Started
Admin Module | Adding Movies,Adding/updating price | Deepak, Indu, Sneha | 25th May | 26th May | 2 | Not Started
Project Name |  | Cinema Café
Start Date |  | 27th May
End Date |  | 30th May
Overall Progress |  | 60%
Developers Team
Task Name | Sub Features | Responsible | Start | End | Days | Status
Sprint 1 |  | Aleena and Team | 27th May | 30th May | 3 | In progress
Booking Module | Seat Booking | Aleena,Venu,Soumya,Ravi,SwamiPrasadam | 27thMay | 29th May | 2 | In progress
Cancel Module | Amount Pay,Cancel Booking | Aleena,Venu,Soumya,Ravi,SwamiPrasadam | 30th May | 30yh May | 1 | Not Started