## Sheet1
Defect Id | Defect Description | Status | Severity | Priority | Identified By | Identified Date | Assigned To | Closed Date | Module | Severity | Status
LM_001 | Title of the Cinema Café page is incorrect | closed | low | low | Deepak | 24/5/2017 | Aleena and Team | 25/05/2017 | Login Module | very high | new
LM_002 | Forgot Password link is misssing | closed | high | medium | Deepak | 24/5/2017 | Aleena and Team | 25/05/2017 | Login Module | high | open
LM_003 | For invalid credentials message is not displayed and page is scrolling to Banner Division | open | medium | low | Deepak | 24/5/2017 | Aleena and Team |  | Login Module | medium | fixed
LM_004 | Password is not Masked | closed | high | high | Deepak | 24/5/2017 | Aleena and Team | 25/05/2017 | Login Module | low | closed
LM_005 | Web page is suggesting User ID and Password | closed | high | high | Deepak | 24/5/2017 | Aleena and Team | 25/05/2017 | Login Module
LM_006 | Spelling Mistakes in displayed text | closed | low | low | Deepak | 24/5/2017 | Aleena and Team | 25/05/2017 | Login Module
LM_007 | Extra Links in the page | closed | medium | medium | Deepak | 24/5/2017 | Aleena and Team | 25/05/2017 | Login Module
LM_008 | Tab sequence of Forgot Password?? And Create New Account is incorrect | fixed | medim | low | Induvardhini | 25/05/2017 | Aleena and Team | 26/05/2017 | Login Module
LM_009 | Label on Forgot Password?? Is incorrect | closed | low | low | Induvardhini | 25/05/2017 | Aleena and Team | 26/05/2017 | Login Module
LM_010 | Label on Create New Account is incorrect | closed | low | low | Induvardhini | 25/05/2017 | Aleena and team | 26/05/2017 | Login Module