## Sheet1
Defect Id | Defect Description | Status | Severity | Priority | Identified By | Identified Date | Assigned To | Closed Date | Module | Severity | Status
UM_001 | Title of Update Movie page is incorrect | fixed | low |  | Deepak | 29/5/2017 | Aleena and team |  | Admin Module | very high | new
UM_002 | Wrong error message for blank date | fixed | medium |  | Deepak | 29/5/2017 | Aleena and team |  | Admin Module | high | open
UM_003 | Movie name is accepting out of range data, number and special characters | fixed | very high |  | Deepak | 29/5/2017 | Aleena and team |  | Admin Module | medium | fixed
UM_004 | Movie is updated for date previous to current date | new | very high | no fix required | Deepak | 29/5/2017 | Aleena and team |  | Admin Module | low | closed
UM_005 | Movie is updated if start time is equals to end time | fixed | very high |  | Deepak | 29/5/2017 | Aleena and team |  | Admin Module
UM_006 | Wrong link is highlighted in the navigation tab | fixed | medium |  | Deepak | 29/5/2017 | Aleena and team |  | Admin Module
UM_007 | Aligmnent of Text boxes is wrong | fixed | medium |  | Deepak | 29/5/2017 | Aleena and team |  | Admin Module
UM__008 | 2 ways to select the date | fixed | medium | no fix required | Deepak | 29/5/2017 | Aleena and team |  | Admin Module
UM_009 | ShowID label is missing | fixed | low |  | Deepak | 29/5/2017 | Aleena and team |  | Admin Module
UM_010 | After updating sucessfully it is not redirecting to any other page | fixed | high | no fix required | Deepak | 29/5/2017 | Aleena and team |  | Admin Module
UM_011 | 9 Extra links - Show All, Design, Development, SEO, go up!!!,facebook,twitter, Google+,Linkedin | fixed | high |  | Deepak | 29/5/2017 | Aleena and team |  | Admin Module