## Sheet1
Cinema Café
23rd May 2017
20%
Developers Team
| Task Name | Activities | Responsible | Start | End | Days | Status
| Sprint 1 |  |  | 22nd May | 26th May | 5 | Inprocess
| DataBase | Database creation | Soumya | 23rd May | 23rd May |  | Completed
| Admin Module | UI | Swami Prasadam | 23rd May | 23rd May |  | Completed
| Admin Module | UI | Ravi Teja | 23rd May | 23rd May |  | Completed
| Admin Module | Connecting to database & validations | Aleena & Venu | 23rd May | 23rd May |  | Completed
Testers Team
| Task Name | Activities | Reported To | Responsible | Start | End | Days | Status
| Sprint 1 |  |  |  | 22th May | 26th May | 5 | In Progress
| Login Module | Designed Automated Test Cases for Cinema Café Page | Aleena and Team | Deepak | 23rd May | 23rd May | 1 | Waiting for Built
| Login Module | Designed Automated Test Cases for Registration Page | Aleena and Team | Sneha | 23rd May | 23rd May | 1 | Waiting for Built
| Login Module | Designed Manual Test Cases for Cinema Café Page | Aleena and Team | Induvardhini | 23rd May | 23rd May | 1 | Waiting for Built
Cinema Café
24th May 2017
30%
Developers Team
Task Name | Task Name | Activities | Responsible | Status
Sprint 1 | Sprint 1 |  |  | Inprocess
DataBase | DataBase | Database creation | Venu | Completed
LoginModule | Admin Module | UI | Swami Prasadam | In Process
Registration Module | Registration Module | Validations | Ravi Teja | Completed
Login & Registration Modules | Forgot Password Page & Update price page | Created the page,Connecting to database & validations | Aleena & Soumya | Completed
Cinema Café
24th May 2017
30%
| Task Name | Activities | Reported To | Responsible | Status
| Sprint 1 |  |  |  | In Progress
| Login Module | Designed Automated Test Cases for Cinema Café Page | Aleena and Team | Deepak | Completed
| Login Module | Designed Automated Test Cases for Registration Page | Aleena and Team | Sneha | Completed
| Login Module | Designed Manual Test Cases for Cinema Café Page | Aleena and Team | Induvardhini | Completed
| Login Module | Designed Manual Test Cases for Registration Page | Aleena and Team | Sneha | Completed
| Login Module | Executed Manual Test Cases for Cinema Café Page | Aleena and Team | Deepak | Completed
| Login Module | Executed Manual Test Cases for Registration Page | Aleena and Team | Induvardhini | Completed
| Login Module | Designed Automated Test Cases for Forgot Password Page | Aleena and Team | Sneha | Completed
| Login Module | Designed Manual Test Cases for Forgot Password Page | Aleena and Team | Induvardhini | Completed
Cinema Café
25th May 2017
50%
Developers Team
| Task Name | Activities | Responsible | Status
| Sprint 1 |  |  | Inprocess
| Validations | Validations & Error messages | Ravi Teja & Venu | Completed
| Add Movies, Update Movies | UI | Swami Prasadam | Completed
| Add Movies,Update Movies | Created the page,Connecting to database & validations | Aleena & Soumya | Completed
Cinema Café
25th May 2017
50%
| Task Name | Activities | Reported To | Responsible | Start | End | Days | Status
| Login Module | Executed Manual Test Cases for Forgot Password Page | Aleena and Team | Sneha | 25th May | 25th May | 1 | Completed
| Login Module | Designed Automated and Manual Test Cases for Edit Profile Page | Aleena and Team | Induvardhini and Sneha | 25th May | 25th May | 1 | Completed
| Login Module | Designed Automated and Manual Test Cases for Add Movies Page | Aleena and Team | Induvardhini and Deepak | 25th May | 25th May | 1 | Completed
| Login Module | Created test script for Cinema Café page | Aleena and Team | Deepak | 25th May | 25th May | 1 | In Progress
Cinema Café
26th May 2017
65%
Developers Team
| Task Name | Activities | Responsible | Status
| Sprint 1 |  |  | Completed
| Validations | Validations & Error messages | Swami Prasadam & Soumya | Completed
| Edit Profile | UI | Ravi Teja | Completed
| Edit Profile | Created the page,Connecting to database & validations | Aleena & Venu | Completed
Cinema Café
26th May 2017
65%
| Task Name | Activities | Reported To | Responsible | Start | End | Days | Status
| Login Module | Executed Manual Test Cases for Edit Profile Page | Aleena and Team | Deepak | 26th May | 26th May | 1 | Completed
| Admin Module | Designed Automated and Manual Test Cases for Update Price Page | Aleena and Team | Induvardhini and Sneha | 26th May | 26th May | 1 | Completed
| Admin Module | Executed Manual Test Cases for Update Price and Add Movie Page | Aleena and Team | Sneha,Induvardhini and Deepak | 26th May | 26th May | 1 | Completed
| Login Module | Executed Automated Test Cases for Cinema Café Page | Aleena and Team | Deepak | 26th May | 26th May | 1 | Completed
Cinema Café
27th May 2017
70%
Developers Team
| Task Name | Activities | Responsible | Status
| Sprint 2 |  |  | InProcess
| Admin Home ,Customer Home | UI | Swami Prasadam & Soumya | Completed
| Show Details | UI | Ravi Teja | Completed
| Show Details | Created the page,Connecting to database & validations | Aleena | Completed
| Validations | Validations and Errors | Venu | In Process
| Task Name | Activities | Reported To | Responsible | Start | End | Days | Status
| Login Module | Created Automated Test Script for Registration Page | Aleena and Team | Induvardhini | 27th May | 27th May | 1 | In Progress
| Login Module | Created Automated Test Script for Forgot Password Page | Aleena and Team | Sneha | 27th May | 27th May | 1 | In Progress
| Admin Module | Created Automated Test Script for Add Movie Page | Aleena and Team | Deepak | 27th May | 27th May | 1 | In Progress
Cinema Café
29th May 2017
70%
Developers Team
| Task Name | Activities | Responsible | Status
| Sprint 2 |  |  | InProcess
| Seat Booking | UI | Soumya & Ravi Teja | Completed
| Seat Booking | Created the page,Connecting to database | Aleena | Completed
| Unit Testing | Creating unit test cases | Venu & SwamiPrasadam | Completed
| Task Name | Activities | Reported To | Responsible | Start | End | Days | Status
| Customer Module | Created and Executed Manual Test Cases for Seat Booking Page | Aleena and Team | Induvardhini | 29th May | 29th May | 1 | Completed
| Admin Module | Executed manual Test Cases for Update Price Page | Aleena and Team | Sneha | 29th May | 29th May | 1 | Completed
| Admin Module | Created and Executed Manual Test Cases for Admin Home And Customer Home Page | Aleena and Team | Deepak | 29th May | 29th May | 1 | Completed