## Sheet1
Project Name |  | ODC system.
Start Date |  | 17th Feb
End Date |  | 24th Feb
Overall Progress |  | 20%
Task Name | Sub Features | Responsible | Start | End | Days | Status
Sprint 1 |  | Chaitanya and Team | 17th Feb | 24th Feb | 7 | In progress
Login Feature |  | Roja,Abhishek, Chaitanya | 17th Feb | 19th Feb | 3 | In progress
Feature 2 |  | Roja,Abhishek, Chaitanya | 20th Feb | 22th Feb | 2 | Not Started
Feature 3 |  | Roja,Abhishek, Chaitanya | 22th Feb | 24th Feb | 2 | Not Started
| exp point | actual point
| 2 | 2
| 4 | 4
| 6 | 0
| 3 | 0
| 5 | 0
| 6 | 0