## Sheet1
|  | PROJECT NAME | Cinema Café
|  | Start Date | 22th May 2017
|  | End Date | 26th May 2017
|  | Overall Progress | 15%
Task Name | Activities | Reported To | Responsible | Start | End | Days | Status
Sprint 1 |  |  |  | 22th May | 26th May | 5 | In Progress
Login Module | Designed Automated Test Cases for Cinema Café Page | Aleena and Team | Deepak | 23rd May | 23rd May | 1 | Waiting for Built
Login Module | Designed Automated Test Cases for Registration Page | Aleena and Team | Sneha | 23rd May | 23rd May | 1 | Waiting for Built
Login Module | Designed Manual Test Cases for Cinema Café Page | Aleena and Team | Induvardhini | 23rd May | 23rd May | 1 | Waiting for Built