## Sheet1
|  | PROJECT NAME | Cinema Café
|  | Start Date | 22th May 2017
|  | End Date | 26th May 2017
|  | Overall Progress | 15%
Task Name | Activities | Reported To | Responsible | Start | End | Days | Status
Sprint 1 |  |  |  | 22th May | 26th May | 5 | In Progress
Login Module | Designed Automated Test Cases for Cinema Café Page | Aleena and Team | Deepak | 23rd May | 23rd May | 1 | Completed
Login Module | Designed Automated Test Cases for Registration Page | Aleena and Team | Sneha | 23rd May | 23rd May | 1 | Completed
Login Module | Designed Manual Test Cases for Cinema Café Page | Aleena and Team | Induvardhini | 23rd May | 23rd May | 1 | Completed
Login Module | Designed Manual Test Cases for Registration Page |  | Sneha | 24th May | 24th May
Login Module | Executed Manual Test Cases for Cinema Café Page |  | Deepak | 24th May | 24th May
Login Module | Executed Manual Test Cases for Registration Page |  | Induvardhini | 24th May | 24th May
Designed Automated Test Cases for Forgot Password Page
Designed Manual Test Cases for Forgot Password Page
Designed Automated Test Cases for Page
Designed Manual Test Cases for Cinema Café Page