## Sheet1
Defect Id | Defect Description | Status | Severity | Priority | Identified By | Identified Date | Assigned To | Closed Date | Module | Severity | Status
EP_001 | Missing Links in Page - Home, Edit Profie, Show details, Cancel Booking, Logout | new | high | high | Deepak | 26/5/2017 | Aleena and Team |  | Login Module | very high | new
EP_002 | For valid data it is redirecting to Cinema Café Page and not showing any messages | fixed | very high | medium | Deepak | 26/5/2017 | Aleena and Team |  | Login Module | high | open
EP_003 | accepting name with Special character | new | medium | medium | Deepak | 26/5/2017 | Aleena and Team |  | Login Module | medium | fixed
EP_004 | accepting passwords which are out of range(8-20) | new | medium | medium | Deepak | 26/5/2017 | Aleena and Team |  | Login Module | low | closed
EP_005 | accepting passwords with special character | new | medium | No fix required | Deepak | 26/5/2017 | Aleena and Team |  | Login Module
EP_006 | accepting Out of range answer(5-100) | new | medium | medium | Deepak | 26/5/2017 | Aleena and Team |  | Login Module
EP_007 | Answer is accepting special character | new | medium |  | Deepak | 26/5/2017 | Aleena and Team |  | Login Module
EP_008 | User details are not Prefilled | new | low | low | Deepak | 26/5/2017 | Aleena and Team |  | Login Module