## Sheet1
Defect Id | Defect Description | Status | Severity | Priority | Identified By | Identified Date | Assigned To | Closed Date | Module | Severity | Status
REG_001 | Title of the Registration page is incorrect | closed | low | low | Induvardhini | 24/5/2017 | Aleena and Team | 25/5/2017 | Login Module | very high | new
REG_002 | Squence of Testbox is Incorrect - User ID should be at second tag | closed | low | low | Induvardhini | 24/5/2017 | Aleena and Team | 25/5/2017 | Login Module | high | open
REG_003 | Unable to Register for Valid Data | closed | very high | high | Induvardhini | 24/5/2017 | Aleena and Team | 25/5/2017 | Login Module | medium | fixed
REG_004 | Web page is displaying previously filled data in each field | closed | medium | low | Induvardhini | 24/5/2017 | Aleena and Team | 25/5/2017 | Login Module | low | closed
REG_005 | For invalid data wrong message is displayed | fixed | medium | low | Induvardhini | 24/5/2017 | Aleena and Team |  | Login Module
REG_006 | Spelling Mistakes in displayed text | closed | low | low | Induvardhini | 24/5/2017 | Aleena and Team | 25/5/2017 | Login Module
REG_007 | Extra Links in the page | closed | medium | low | Induvardhini | 24/5/2017 | Aleena and Team | 25/5/2017 | Login Module
REG_008 | Question label is missing | closed | high | low | Sneha | 24/5/2017 | Aleena and Team | 25/5/2017 | Login Module
REG_009 | Position of Register Button is changing after clicking | closed | low | low | Sneha | 24/5/2017 | Aleena and Team | 25/5/2017 | Login Module
REG_010 | Label on Mobile textbox is incorrect | closed | low | low | Sneha | 24/5/2017 | Aleena and Team | 25/5/2017 | Login Module
REG_011 | Label on User ID textbox is incorrect | open | low | No fix required | Sneha | 24/5/2017 | Aleena and Team |  | Login Module
REG_012 | Label on Password textbox is incorrect | closed | low | low | Sneha | 24/5/2017 | Aleena and Team | 25/5/2017 | Login Module
REG_013 | Label on Answer textbox is incorrect | closed | low | low | Sneha | 24/5/2017 | Aleena and Team | 25/5/2017 | Login Module
REG_014 | Label on Register button is incorrect | closed | low | low | Sneha | 24/5/2017 | Aleena and Team | 25/5/2017 | Login Module
REG_015 | Unexpected pop up on clicking on Register button | closed | medium | medium | Induvardhini | 26/5/2017 | Aleena and Team | 28/5/2017 | Login Module
REG_016 | accepting Digits and special characters for Names | fixed | medium | medium | Induvardhini | 26/5/2017 | Aleena and Team | 28/5/2017 | Login Module
REG_017 | Wrong message is displyed If Answer is out of range | new | low |  | Deepak | 28/5/2017 | Aleena and Team
REG_018 | Textboxes are not properly aligned | fixed | low |  | Induvardhini | 29/05/2017 | Aleena and Team |  | Login Module