## Sheet1
Defect Id | Defect Description | Status | Severity | Priority | Identified By | Identified Date | Assigned To | Closed Date | Module | Severity | Status
UM_001 | links are missing Home,Add Movie,Update Movie,Update Price,LOGOUT | fixed | high | high | Sneha | 26/05/2017 | Aleena and team |  | Admin Module | very high | new
UM_002 | Extra links are added like CANCEL,go up!!! | fixed | high | medium | Sneha | 26/05/2018 | Aleena and team |  | Admin Module | high | open
UM_003 | labels missed for start and end time | fixed | medium | medium | Sneha | 26/05/2019 | Aleena and team |  | Admin Module | medium | fixed
UM_004 | moive is updating for the invalid data | new | high | high | Sneha | 26/05/2020 | Aleena and team |  | Admin Module | low | closed
UM_005 | label name of Show Id is incorrect | fixed | low | low | Sneha | 26/05/2021 | Aleena and team |  | Admin Module
UM_006 | label name of Movie Name is incorrect | fixed | low | low | Sneha | 26/05/2022 | Aleena and team |  | Admin Module
UM_007 | Error messages for invalid data is incorrect | fixed | medium | low | Sneha | 26/05/2023 | Aleena and team |  | Admin Module
UM_008 | 2 ways to select date, only calender is expectd | new | medium | low | Deepak | 26/05/2023 | Aleena and team |  | Admin Module
UM_009 | Spelling Mistakes in displayed text | fixed | low | low | Induvardhini | 26/05/2023 | Aleena and team |  | Admin Module