## Sheet1
Defect Id | Defect Description | Status | Severity | Priority | Identified By | Identified Date | Assigned To | Closed Date | Module | Severity | Status
UP_001 | label is not present at the Seat type | closed | medium | low | Induvardhini | 26/05/2017 | Aleena and team | 29/5/2017 | Admin Module | very high | new
UP_002 | Missing links according to the page specification | closed | high | medium | Induvardhini | 26/05/2017 | Aleena and team | 29/5/2017 | Admin Module | high | open
UP_003 | LOGOUT link is redirecting to Admin Home Page rather than Cinema Café page | closed | high | high | Induvardhini | 26/05/2017 | Aleena and team | 29/5/2017 | Admin Module | medium | fixed
UP_004 | label on Price is incorrect | closed | low | low | Induvardhini | 26/05/2017 | Aleena and team | 29/5/2017 | Admin Module | low | closed
UP_005 | Title of Update Price page is incorrect | closed | low | low | Induvardhini | 26/05/2017 | Aleena and team | 29/5/2017 | Admin Module
UP_006 | extra link is present - go up | new | low |  | Sneha | 29/05/2017 | Aleena and team |  | Admin Module
UP_007 | Follow us on label is not required | new | low |  | Sneha | 29/05/2017 | Aleena and team |  | Admin Module
UP_008 | Error messages are not according to page specifications | new | medium |  | Sneha | 29/05/2017 | Aleena and team |  | Admin Module
UP_009 | Label on Seat Type and Price are not visible | new | low |  | Deepak | 29/05/2017 | Aleena and team |  | Admin Module
UP_010 | Label on Seat Type, Price and update are not properly alligned | new | low |  | Deepak | 29/05/2017 | Aleena and team |  | Admin Module